## Sheet1
| ANTICIPATED CONSTRUCTION SCHEDULE | [14 empty] | SUMMER 2011 | [18 empty] | R.C.S.D. School of the Arts
WORK ITEMS |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY | [5 empty] | JUNE |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER
|  | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
ALL CONTRACTS
BIDS DUE
S.E.D. APPROVAL
CONTRACT AWARDED
SHOP DRAWING REVIEW
MATERIAL ACQUISITION
CONST'N TIME FRAME
CLEAN-UP
PUNCH LIST ITEMS
Auditorium Sound Booth
Removals GC, M, E
Concrete
Walls
Finishes
Mechanical
Electrical
Lobby Display
Removals
Framing
Finishes
Electrical
Entry Doors
Removals
Installation
Electrical
Flooring
Removals
Installation
Clock Replacement
Removals
Replacement
Security Cameras
Installation
Testing
Training
Alternates
Display Case
Atrium Doors
Note on O3: Hansen, Eric:
STUDENTS LEAVE JUNE 23rd
CONSTR'N START JUNE 27th
TEACHERS LEAVE JUNE 24th
TEACHERS RETURN AUG 31st
STUDENTS RETURN AUG 5th
SUB'L COMPLETION AUG 24th